## Sheet1
Name: | Tomas Umholtz
Course: | Dev119
Section: | One
Hourly Rate | 45
Time in Hours | Estimate | Actual | Difference
Week 1 | 15 | 36.5 | 21.5
Billing | 675 | 1642.5 | -967.5
Review Activities | 1 | 4 | 3
A Course for Confidence | 1 | 3 | 2
GTT | 1 | 1.5 | 0.5
Anchor Points | 1 | 3 | 2
Development | 2 | 5 | 3
Call to Success | 2 | 4 | 2
Time Management Worksheet | 2 | 3 | 1
P & P 1 | 1 | 4 | 3
Burn-Up List | 2 | 3 | 1
Other | 2 | 6 | 4
Week 2 | 24.9 | 24.4 | 0.5
Billing | 1120.5 | 1098 | 22.5
Review Activities | 0.2 | 0.2 | 0
Complete Assingments For Review | 0.2 | 0.2 | 0
Call to Action (Total) | 2 | 5 | 3
Mission Statement | 2 | 1.5 | -0.5
Methodology | 2 | 1.5 | -0.5
Project Planning | 2 | 1.5 | -0.5
Research | 2 | 3 | 1
Development | 2 | 1.5 | -0.5
SWOT | 3 | 2 | -1
P & P 2 | 5 | 3.5 | -1.5
Burn-Up List | 1 | 1 | 0
Career Module | 3 | 3 | 0
Time Management Worksheet | 0.5 | 0.5 | 0
Week 3 | 23.7 | 23.7 | 0
Billing | 1066.5 | 1066.5 | 0
Review Assingments | 0.2 | 0.4 | -0.2
Complete Assingments For Review | 0.3 | 0.3 | 0
GTT | 1 | 1.3 | -0.3
Call to Action (Total) | 4 | 4 | 0
Communicating with Clarity | 2 | 2 | 0
Communicating with Visual Tools | 2 | 2 | 0
Development | 2 | 1 | 1
P & P 3 | 4 | 5 | -1
Burn-Up List | 1 | 1.5 | -0.5
Career Module | 2 | 2 | 0
Time Management Worksheet | 0.2 | 0.2 | 0
Other | 5 | 4 | 1
Total Billing | 2862 | 3807 | -945